## Project Overview
VSA Advisor Bot — Project Completion Dashboard
Workplan status as at 17 August 2026, with a fixed final submission deadline of 28 September 2026.
Submission Date |  |  | Calendar Days Remaining |  | Completed Tasks | In Progress | Overall Plan Completion
2026-09-28 |  |  | 42 |  | 14 | 0 | 69.17%
Critical path to submission
Window | Priority | Required Output | Decision Gate | Schedule safeguards
20 Aug–3 Sep | Collect real user data | 10–15 signed/coded sessions | Minimum 10 genuine participants | • Recruitment starts before literature/report rewriting is finished so work proceeds in parallel.
4–8 Sep | Analyse and improve | Dashboard, themes and change log | Every change justified by evidence | • Feature freeze on 18 September protects the evidence and MP4 from late technical changes.
1–17 Sep | Rewrite report | Methods, results and limitations | All thresholds/citations traceable | • MP4 completes seven days before submission, leaving time for format/playback correction.
14–21 Sep | Capture evidence and MP4 | Final screenshots and 3–5 min MP4 | Playback and format verified | • Supervisor changes have a two-day bounded window before packaging.
19–25 Sep | Quality and feedback | Rubric audit and corrections | Supervisor changes closed | • Final package is tested and backed up one day before submission.
26–28 Sep | Package and submit | Backup, upload and receipt | Submit by 28 September | • Historic estimates remain visibly labelled and should be replaced with actual records where available.
Examiner alignment: this workbook supplies the missing complete/feasible workplan, makes dependencies visible, and creates a dated route to the required MP4 and final submission.

## Settings
Project Planning Assumptions
Confirmed dates and reconstructed estimates are explicitly separated so the workplan can be corrected without hiding uncertainty.
Status date | 2026-08-17
Estimated project start | 2026-05-04
Final submission deadline | 2026-09-28
Target user-study sample | 15
Date confidence definitions
Estimate | Reconstructed historic planning date; replace with documentary evidence if available.
Confirmed | Date supported by a completed artifact or evidence captured in the project.
Planned | Forward schedule used to reach the final submission.
Fixed | External deadline that must not move.

## Workplan
VSA Advisor Bot — Complete Workplan
Historic dates marked Estimate are editable; the forward plan is scheduled to the fixed 28 September 2026 submission.
ID | Phase | Task | Start | End | Duration (days) | Status | % Complete | Owner | Predecessor(s) | Deliverable / Evidence | Date Confidence | Notes
1 | Foundation | Select Template 4.2 and define the financial-advisor concept | 2026-05-04 | 2026-05-15 | 12 | Complete | 100% | Student | — | Template alignment and project concept | Estimate | Historic date reconstructed; replace if records exist.
2 | Foundation | Identify target users, problem, ethical scope and non-advice boundary | 2026-05-11 | 2026-05-22 | 12 | Complete | 100% | Student | 1 | User/domain requirements | Estimate | Core responsible-finance scope.
3 | Strategy | Elicit and formalise mirrored VSA CAB Scenarios 1–3 | 2026-05-18 | 2026-05-29 | 12 | Complete | 100% | Student | 2 | Formal VSA rule specification | Estimate | Thresholds now implemented consistently.
4 | Research | Draft literature review, architecture and evaluation strategy | 2026-05-18 | 2026-06-19 | 33 | Complete | 100% | Student | 1 | Initial literature and design chapters | Estimate | Requires later strengthening and citation audit.
5 | Prototype | Build feature prototype and submit preliminary report | 2026-06-01 | 2026-06-29 | 29 | Complete | 100% | Student | 3,4 | Preliminary report and prototype | Confirmed | Report filename records 29 June.
6 | Data | Acquire, clean and validate XAUUSD five-minute data | 2026-06-30 | 2026-07-10 | 11 | Complete | 100% | Student | 5 | Clean M5 dataset | Estimate | 143,020 bars available in current evidence.
7 | ML | Extract formal VSA setups and generate outcome labels | 2026-07-06 | 2026-07-20 | 15 | Complete | 100% | Student | 3,6 | 431 labelled formal setups | Estimate | VSA determines candidates; labels measure 1R-before-stop.
8 | ML | Train Logistic Regression and Random Forest separately | 2026-07-20 | 2026-08-03 | 15 | Complete | 100% | Student | 7 | Separate LR and RF models/results | Estimate | Examiner requirement met.
9 | ML | Tune validation thresholds, compare baselines and select LR | 2026-08-01 | 2026-08-07 | 7 | Complete | 100% | Student | 8 | Model comparison and selection evidence | Confirmed | LR selected for validation performance and explainability.
10 | Product | Build Streamlit advisor, explanation and evaluation pages | 2026-07-27 | 2026-08-10 | 15 | Complete | 100% | Student | 8 | Non-technical web interface | Estimate | ML Advisor performance was subsequently optimised.
11 | Integration | Implement MT5 CSV bridge, M5 exporter and risk controls | 2026-08-07 | 2026-08-17 | 11 | Complete | 100% | Student | 9,10 | Compiled EAs and desktop/mobile alerts | Confirmed | Includes stale-signal, news and WATCH_ONLY controls.
12 | Evaluation | Run automated, replay, robustness and cost-sensitivity tests | 2026-08-10 | 2026-08-17 | 8 | Complete | 100% | Student | 9,11 | Test logs and evaluation evidence | Confirmed | Negative walk-forward evidence retained honestly.
13 | User study | Prepare participant information, signed consent and questionnaire | 2026-08-17 | 2026-08-17 | 1 | Complete | 100% | Student | 10,12 | Two verified DOCX study instruments | Confirmed | No participant data fabricated.
14 | Management | Create analysis workbook, full workplan and Gantt evidence | 2026-08-17 | 2026-08-19 | 3 | Complete | 100% | Student | 13 | Analysis and planning workbooks | Confirmed | Analysis and planning workbooks verified.
15 | User study | Recruit and run 10–15 genuine target-user sessions | 2026-08-20 | 2026-09-03 | 15 | Not started | 0% | Student | 13,14 | Signed forms and coded questionnaires | Planned | Prioritise novice/interested traders and relevant students.
16 | User study | Analyse responses and implement justified usability improvements | 2026-09-04 | 2026-09-08 | 5 | Not started | 0% | Student | 15 | Survey tables, charts and change log | Planned | Use aggregate data and anonymised comments.
17 | Research | Strengthen literature comparison and complete citations for facts/visuals | 2026-08-20 | 2026-09-08 | 20 | Not started | 0% | Student | 4,12 | Revised critical literature review | Planned | Compare related systems, ML/XAI and VSA evidence.
18 | Report | Rewrite methodology, design and implementation chapters | 2026-09-01 | 2026-09-12 | 12 | Not started | 0% | Student | 12,17 | Traceable methods/design chapters | Planned | Include feature table, pseudocode and consistent thresholds.
19 | Report | Write results, evaluation, limitations and future work | 2026-09-09 | 2026-09-17 | 9 | Not started | 0% | Student | 16,18 | Evidence-led evaluation chapter | Planned | Separate test, robustness and user-study conclusions.
20 | Evidence | Capture final website, LR/RF, testing and MT5 screenshots | 2026-09-14 | 2026-09-18 | 5 | Not started | 0% | Student | 16,19 | Numbered evidence appendix | Planned | Every visual requires a caption and source.
21 | Demonstration | Script, record and edit the required 3–5 minute MP4 | 2026-09-16 | 2026-09-21 | 6 | Not started | 0% | Student | 19,20 | Compliant MP4 demonstration | Planned | Show VSA→LR→CSV→MT5 and safety controls.
22 | Quality | Run report QA: references, word count, coherence and rubric mapping | 2026-09-19 | 2026-09-23 | 5 | Not started | 0% | Student | 19,20,21 | Submission-quality report | Planned | Check every examiner point explicitly.
23 | Quality | Apply final supervisor/teacher feedback | 2026-09-24 | 2026-09-25 | 2 | Not started | 0% | Student | 22 | Approved corrections | Planned | Keep a two-day bounded correction window.
24 | Submission | Package report, MP4, workplan, code and backups | 2026-09-26 | 2026-09-27 | 2 | Not started | 0% | Student | 23 | Validated submission package | Planned | Open every file from the final package before upload.
25 | Submission | Submit final project | 2026-09-28 | 2026-09-28 | 1 | Not started | 0% | Student | 24 | Final submission receipt | Fixed | 28 September 2026 deadline.

## Gantt
Weekly Gantt Chart
Project period: May–September 2026. Green = complete, amber = in progress, blue = planned; submission is fixed on 28 September.
Project timeline: May to September 2026 |  |  |  |  | May 2026 |  |  |  | June 2026 |  |  |  |  | July 2026 |  |  |  | August 2026 |  |  |  |  | September 2026
Phase | Task | Start | End | Status | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28
Foundation | Select Template 4.2 and define the financial-advisor concept | 2026-05-04 | 2026-05-15 | Complete | 2026-05-04: 3; 2026-05-11: 3
Foundation | Identify target users, problem, ethical scope and non-advice boundary | 2026-05-11 | 2026-05-22 | Complete | 2026-05-11: 3; 2026-05-18: 3
Strategy | Elicit and formalise mirrored VSA CAB Scenarios 1–3 | 2026-05-18 | 2026-05-29 | Complete | 2026-05-18: 3; 2026-05-25: 3
Research | Draft literature review, architecture and evaluation strategy | 2026-05-18 | 2026-06-19 | Complete | 2026-05-18: 3; 2026-05-25: 3; 2026-06-01: 3; 2026-06-08: 3; 2026-06-15: 3
Prototype | Build feature prototype and submit preliminary report | 2026-06-01 | 2026-06-29 | Complete | 2026-06-01: 3; 2026-06-08: 3; 2026-06-15: 3; 2026-06-22: 3; 2026-06-29: 3
Data | Acquire, clean and validate XAUUSD five-minute data | 2026-06-30 | 2026-07-10 | Complete | 2026-06-29: 3; 2026-07-06: 3
ML | Extract formal VSA setups and generate outcome labels | 2026-07-06 | 2026-07-20 | Complete | 2026-07-06: 3; 2026-07-13: 3; 2026-07-20: 3
ML | Train Logistic Regression and Random Forest separately | 2026-07-20 | 2026-08-03 | Complete | 2026-07-20: 3; 2026-07-27: 3; 2026-08-03: 3
ML | Tune validation thresholds, compare baselines and select LR | 2026-08-01 | 2026-08-07 | Complete | 2026-07-27: 3; 2026-08-03: 3
Product | Build Streamlit advisor, explanation and evaluation pages | 2026-07-27 | 2026-08-10 | Complete | 2026-07-27: 3; 2026-08-03: 3; 2026-08-10: 3
Integration | Implement MT5 CSV bridge, M5 exporter and risk controls | 2026-08-07 | 2026-08-17 | Complete | 2026-08-03: 3; 2026-08-10: 3; 2026-08-17: 3
Evaluation | Run automated, replay, robustness and cost-sensitivity tests | 2026-08-10 | 2026-08-17 | Complete | 2026-08-10: 3; 2026-08-17: 3
User study | Prepare participant information, signed consent and questionnaire | 2026-08-17 | 2026-08-17 | Complete | 2026-08-17: 3
Management | Create analysis workbook, full workplan and Gantt evidence | 2026-08-17 | 2026-08-19 | Complete | 2026-08-17: 3
User study | Recruit and run 10–15 genuine target-user sessions | 2026-08-20 | 2026-09-03 | Not started | bar: 2026-08-17 to 2026-08-31
User study | Analyse responses and implement justified usability improvements | 2026-09-04 | 2026-09-08 | Not started | bar: 2026-08-31 to 2026-09-07
Research | Strengthen literature comparison and complete citations for facts/visuals | 2026-08-20 | 2026-09-08 | Not started | bar: 2026-08-17 to 2026-09-07
Report | Rewrite methodology, design and implementation chapters | 2026-09-01 | 2026-09-12 | Not started | bar: 2026-08-31 to 2026-09-07
Report | Write results, evaluation, limitations and future work | 2026-09-09 | 2026-09-17 | Not started | bar: 2026-09-07 to 2026-09-14
Evidence | Capture final website, LR/RF, testing and MT5 screenshots | 2026-09-14 | 2026-09-18 | Not started | bar: 2026-09-14
Demonstration | Script, record and edit the required 3–5 minute MP4 | 2026-09-16 | 2026-09-21 | Not started | bar: 2026-09-14 to 2026-09-21
Quality | Run report QA: references, word count, coherence and rubric mapping | 2026-09-19 | 2026-09-23 | Not started | bar: 2026-09-14 to 2026-09-21
Quality | Apply final supervisor/teacher feedback | 2026-09-24 | 2026-09-25 | Not started | bar: 2026-09-21
Submission | Package report, MP4, workplan, code and backups | 2026-09-26 | 2026-09-27 | Not started | bar: 2026-09-21
Submission | Submit final project | 2026-09-28 | 2026-09-28 | Not started | bar: 2026-09-28

## Milestone Timeline
Milestone Timeline
Major evidence points and remaining deadlines, ordered toward the fixed 28 September submission.
Milestone | Date | Status | Evidence / Output | Days from Project Start
Template and concept confirmed | 2026-05-15 | Complete | Template 4.2 alignment | 11
Formal VSA scenarios specified | 2026-05-29 | Complete | Mirrored scenario rules | 25
Preliminary report submitted | 2026-06-29 | Complete | Prior report | 56
M5 dataset prepared | 2026-07-10 | Complete | 143,020 bars | 67
LR/RF comparison and LR selection | 2026-08-07 | Complete | Separate model evidence | 95
MT5 bridge and live exporter verified | 2026-08-17 | Complete | Compile/runtime screenshots | 105
Consent and questionnaire verified | 2026-08-17 | Complete | Two user-study DOCX forms | 105
Target-user sessions complete | 2026-09-03 | Planned | 10–15 coded responses | 122
Evaluation/report content complete | 2026-09-17 | Planned | Revised results and limitations | 136
MP4 demonstration complete | 2026-09-21 | Planned | 3–5 minute MP4 | 140
Submission package validated | 2026-09-27 | Planned | Final backup and file-open test | 146
Final submission | 2026-09-28 | Fixed | Submission receipt | 147

## Risks and Controls
Risks and Controls
The remaining plan protects the final submission date by assigning owners, mitigation and trigger dates.
Risk | Likelihood | Impact | Control / Mitigation | Trigger Date | Owner | Status
Insufficient genuine participants | Medium | High | Recruit early, use relevant student/trader groups, track daily toward minimum 10. | 2026-08-27 | Student | Open
Citation gaps remain | Medium | High | Run claim-by-claim citation audit and replace weak/non-academic sources. | 2026-09-05 | Student | Open
Website or MT5 demo instability | Low | High | Record controlled replay, retain compile/runtime evidence and create local backup inputs. | 2026-09-14 | Student | Controlled
MP4 rejected for format/length | Low | High | Export MP4, verify 3–5 minutes and test playback on another device. | 2026-09-21 | Student | Open
Report exceeds word limits | Medium | Medium | Maintain chapter word-count table and edit before supervisor review. | 2026-09-22 | Student | Open
Late changes damage final package | Medium | High | Freeze features after 18 September; use final checklist and redundant backups. | 2026-09-24 | Student | Open